## Sheet1
Date: | Issue: | Posted By: | Proposed Resolution:
2019-04-08 | Will we record the usability testing sessions? | Caroline | no.
| Should teachers be able to create multiple boards/spaces for different classes? | Caroline | For usability testing, turn off account set-up screen (make board for each class, enter email, etc)
| LONG-TERM: Which screens will we attempt to code? | Caroline
| LONG-TERM: How do we want to maximize using GitHub with this project? | Caroline
| What data samples should we use for the prototype? | Caroline
| Alt text/caption ability for photo upload? | Caroline
| What specific elements of 508 compliance do we want to highlight in our presentations (and in our accessibility statement)? | Ericka
| Make "Usability Testing" spreadsheet for responses etc. | Caroline
| How will we keep data secure [other than password protection] | Ericka
| How should we address the issue of student consent/agency over the data collected on them? | Ericka
2019-04-12 | Need to clarify "swipe right" and "swipe left" (is "left" the motion in which your're swiping, or the direction in which you're heading?); find language that is clear but also aligns with norms of what left and right are | Caroline
| Need a way to symbolize "swiping" back left or right to get back to home screen (color semi-circle??) | Caroline
2019-04-15 | Need to add "create boards for different classes" in tutorial and in interface | Caroline
| Need to clarify tutorial sequence with customizing settings | Caroline
| Need to decide input/output terms | Caroline
| Need to pick consisted transitions for X-ing out, sliding back Home, etc. | Caroline
| Is term going to be too ambitious for our scope? Kind of hard to make "airtight" rn | Caroline | Yes, we will stick with user defining date range
| Need to figure out exactly what this output graph will look like | Caroline | Will go into more detail for presentation
| Swiping doesn't work on prototype (it gets confused); tapping only! | Caroline | Tappity tap tap
| Should we move settings wheel to the top? It's hard to go back to where you were if you accidentally click it | Caroline | Can move to top right, don't need to include on "pop-up" screens